## Allocation
Sl No. | Civic Agencies | Priority | Interns | Internal Resource (for initial meetings) | Status
1 | BBMP | 1 | Jeevan | Ramya | Inprogress
2 | BWSSB | 1 | Rahul | Madhva | Inprogress
3 | BMTC | 1 | Rahul | Madhva | Inprogress
4 | BMRCL | 1 | Jasmeen | Kiran | Inprogress
5 | BESCOM | 1 | Jasmeen | Kiran | Inprogress
6 | BTP | 1 | Jeevan | Ramya | Inprogress
7 | BCP | 1 | Jeevan | Ramya | Inprogress
8 | BDA | 2 | Rahul | Madhva | Inprogress
9 | BMRDA | 2 | Rahul | Madhva | Not Started | Commissioner BMRDA
10 | DULT | 2 | Jasmeen | Ramya | Not Started
11 | KSNDMC | 1 | Jasmeen | Ramya | Inprogress
12 | KSPCB | 1 | Heena | Ramya | Inprogress
13 | KFD | 2 | Jasmeen | Ramya | Not Started | Prasanna, IT - 9449703704, | Lekha darshini, IT Wing Manager - 9740940822
14 | KF&ES | 1 | Heena | Ramya | Not Started
15 | Transport Dept | 2 | Heena | Ramya | Not Started | Hemanth Kumar - 22235176
16 | Health Dept | 1 | Rahul | Madhva | Inprogress
17 | Education Dept | 2 | Jeevan | Kiran | Not Started | Shalini Rajinish, Principal Secretary
18 | Tourism Dept | 2 | Rahul | Madhva | Inprogress
19 | Horticulture | 2 | Heena | Madhva | Not Started | Dr. Jagadish, Joint Director - 9845242482
20 | BIAL | 2 | Jeevan | Kiran | Not Started
21 | BIAAPA (Bangalore International Airport Area Planning Authority) | 2 | Jeevan | Kiran | Not Started
22 | KSRTC | 2 | Heena | Kiran | Not Started | Jagadeesha Chandra, CCE - 7760990200
23 | LDA / Minor Irrigation | 2 | Jasmeen | Ramya | Not Started
24 | e-Governance / ITBT | 3
25 | Food and Civil Supllies | 3
26 | Railways | 3
27 | PWD | 3
28 | NHAI | 3
29 | KSDB (Karnataka Slum Development Board) | 3
30 | BMLTA (Bengaluru Metropolitan Land Transport Authority) | 3
31 | BMICPA - Bengaluru Mysuru Corridor | 3
32 | KUIDFC | 3
33 | NIC -MEITY |  |  |  |  | State Information Officer
KIADB
Directorate of Town and Country Planning
Wednesday 11Am - Metro Visit
Monday 11 Am give call to Harishekharan Sir - to fix up appointment after 26th
Monday 3 PM - Manoranjan Hegde - Health Dept BBMP
---------------------------
Forest Department - Wednesday 3 PM or Thursday morning

## BBMP
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1 | 2019-06-04 | BBMP - Projects | Mr. Ravikuamr IAS, Special Commissioner BBMP | Shantveer, Ramya and Jeevan | Based on the interaction he has asked us to take up the below projects on priority 1. SWM – Fleet Management Syste 2. Fire Services – Fleet Management System 3. Storm Water Drains – Disaster Management System ( 100 sensors provided by KSNDMC, also drone survey is being done for disaster management) 4. Street Lighting – As the tender is already out, we can check on integrating data in phases 5. Roads Management and Pothole Monitoring system – He has asked us to check on the c Vigil app on its working The below based on further discussions with specific departments 6. Animal Husbandry 7. Health Management For SWM and Animal Husbandry Mr. Randeep, IAS can be contacted. For the rest he will let us know on specific persons to be contacted and asked us to start the activities ASAP from Thursday (since tomorrow being government holiday) We also enquired on meeting with Mr.Seshadri for which he has confirmed that Mr.Randeep is incharge of the IT cell of BBMP and we can interact with him for any details.
2 | 2019-06-07 | SWM, Welfare | Mr. Randeep IAS, Special Commisioner BBMP | Ramya, Jeevan | 1. As ICCC will take atleast another year to be Live and they wanted to see some progress on the SWM, the department is getting ready with a phase 1 tender (only for fleet management)to be floated this week. 2. He would like us to review the tender to check if there is anything needed to be added for integration with ICCC and also advise for any functionality which was missed. 3. Manjula from SWM department is working on the document and I am yet to receive it from her. Will share it once I receive it. 4. The next phases/improvements in the SWM, he would like to take it along with ICCC. Ms. Manjula will be nodal person for contact. 5. Animal Husbandry – They have some IT system which is already developed along with an app called Shwana. He has asked us to meet Mr. Shashikumar, New Joint Director for further details on this. There is also one new tender which is getting floated for this which is again for fleet management of the vans used for catching dogs. 6. He said IT and Finance is not under him anymore
3 | 2019-06-12 | Animal Husbandry | Mr. Shashikumar, Joint Director | Ramya | 1. An app called Shwana App is planned and tendered out. 2. A tender is out for Animal Birth Control Monitoring which is available on the e-procurement website as on date 22/2/2019. 3. Mr. Shashikumar requested to cehck if a e-challan system can be done through ICCC for the department. Basically used for Inspection at zone level for Chicken/Mutton Stall and fines for Stray Cattle
4 | 2019-06-20 | Roads and Pothole Street Light | Mr. Madhu Kumar | Ramya, Jeevan | Roads and Pothole Management - He confirmed that currently there is no IT system available. He shared the zonal level engineer numbers and asked us to contact them for more details. Roads History is one of IT system which can be checked. Street Light -Currently there are no IT systems available for monitoring of street lights. A tender is out for transformation of street light with LED lighting. A engineer is getting appointed to check on Energy savings by the department through this initiative (we could get more details once this is done) A list of zonal level engieers was given and asked us to cehck with them for more details.
5 | 2019-06-26 | Health dept in BBMP | Dr.Suresh | Ramya, Jeevan | Discussed and explained about the smart city project and he also introduced us to IT Admin Gulzaar who will inturn be the In-charge person of the IT dept.
| 2019-06-27 | Health dept in BBMP | Ms.Gulzaar | Jeevan | •She shared the entire details of IT solutions in regards to Health dept in BBMP. •She shared soft copy of the six referral hospitals details. •She also explained about the working of Lab software,website and portal used. •She also gave the demo of each Lab machine which is located in H.Siddaiah referral Hospital. •She also briefed me about the server used to maintain the record of the patients,staffs and doctors.
|  | Road and Pothole Management | Madhu Kumar - 9480683613
Storm Water Drains - Shiva Prasad H M - 9739094360
Street Lighting - Madhu Kumar - 9480683613
Health Management - Dr Manorajanan Hegde - 9480683928

## BCP
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1 | 2019-11-06 | BCP | Mr. Anucheth IPS, DCP | Ramya and Jeevan | Introduced us to Mr.AjayKumar who will inturn be the nodal officer to take us to the different departments within BCP and introducing to the vendors involved in the IT systems in BCP. Many of the initiatives are planned with the Nirbhaya fund available. A document is to be shared for further details on Nirbhaya. An app called 3rd eye which integrates around 23 databases like ration, aadhar, crime. water and electricity connection etc, is used in Telengana which could be very useful to officials to get data of citizens.
2 | 2019-12-06 | BCP | Mr. Ajaykumar, ACP | Ramya and Jeevan | Introduced Rajath who will inturn be the In-charge person IT-dept and also introduced to Trimax and Matrix vendors, also introduced to the CCRB wing for data collection
3 | 13/6/2019 | BCP | Mr.Rajath | Jeevan | •Call centre : He explained the current flow to data. •Dispatch Management : He briefed about the GIS layer they use to map the hoysala. •Dial 100 : He briefed about the Dashboard used to monitor different sectors of issues.
4 | 17/6/2019 | BCP | Mr.Prasad | Jeevan | •Met the In-charge person of the Surveillance dept •Collected the required data about the camera specifications and etc..
5 | 17/6/2019 | BCP | Mr.Ravi | Jeevan | •Met the In-charge person of social media dept •Collected the required data about the Dashboard used to monitor social media.
6 | 18/6/2019 | BCP | Mr.Ramesh | Jeevan | •Met the In-charge person of CCRB dept in BCP and he briefed me about the process. •Briefed me about the website and the records which are maintained in BCP. •He also Expalined me about the E-governace applications such as E-lost.
7 | 18/6/2019 | BCP | Ms.Preethi | Jeevan | •Discussed about the grievance Management in BCP and also about other organisations such as MAKALA SAHAYAVANI and VANITHA SAHAYAVANI.

## Health Dept
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1 | 2019-06-07 | Health | Mr.Prabhudeva Gowda | Madhva and Rahul | Mr Arun Kumar ( DD for ehospital ), who is the contact point for all data /services related information is on training for next 4 weeks and we met Addln incharge Mr. Prabhudeva Gowda ( DD for Child health, additional charge for e-hospital also) Also contact Praveena 7829824648 for any information, meetings. Introduced Rahul from ideck for further data collection. Briefed Mr Prabhudeva on ICCC and informed on our planned activities in this regard. He has requested Govt. Order for this activity and we can also send Checklist/Questionnaire to these email ids for taking it further Questionnaire to be sent to Ddehospital-hfws@karnataka.gov.in snonuhmkar@gmail.com

## BESCOM
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions

## BWSSB
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions

## BMRCL
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1 | 2019-06-04 | BMRCL |  | Kiran and Jasmeen
Executive director - 25191042 - Shankar

## BMTC
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1

## KSPCB
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1 | 2019-06-18 | KSPCB | Mr. N M Raju Dr. Lokeshwari
2 | 2019-06-18 | KSPCB, Grievance Management | Mr. Prbhudeva

## KSNDMC
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1 | 2019-06-14 | KSNDMC | Dr.Shubha |  | KSNDMC has a very good IT Infrastructure and data from the department could be directly integrated to the ICCC which will help information dissemination to various stakeholders and to the citizens and for further analytics with data received from other departments too. Below are a few points based on our initial discussions 1. 100 Telemetric Rain Gauges and 6 Telemetric Weather Sensors (+4 in pipeline) which are solar powered GPRS enabled device which provides data at 15 minutes interval. These have been installed in government buildings like department offices, bus depots, etc. 2. Varunamithra is a new app introduced which gives live information to citizens 24/7. 3. 201 Flood vulnerable areas have been identified by the technology of Hydrological model. 4. Be Ready Bengaluru is a whatsapp group which is used for dissemination of weather related information to Citizens and Bengaluru. 5. The department has a well-established GIS which is mapped on the ESRI platform. 6. A call centre is available within the department which works 24/7. 7. Everyday reports are sent to various stakeholders like BBMP, Traffic, BESCOM, BWSSB, etc. on various information extracted from the systems. A detailed meeting is planned where the different data feeds, reports will be shared with the PMC

## BTP
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
1 | 2019-06-24 | BTP | Mr. Harishekharan, IPS Additional Commisioner of Traffic Police | Ramya and Jeevan | Breifed on the project and Bengaluru Smart City. We have to seek time and make a presentation on the projects of Bengaluru Smart City. Since TMC has already evolved, we should be considering them for any inputs for the city level project. Ramya to take an appointment on 26th or 27th to meet him along with Shantveer to make a presentation He introduced to Mr. Mustafa with whom all details on existing system can be collected
2 | 2019-06-25 | BTP | Mr. Mustafa | Ramya and Jeevan | Gave the details on existing IT systems in BTP. Further meetings are to be held for data acquisition
3 | 2019-06-26 | BTP | Mr.Mustafa | Jeevan | Collected the soft copy of the data like Numbr of cameras, location and vendors details.
4 | 2019-06-27 | BTP | Mr.Mustafa and Mr.khan | Jeevan | Breified about data flows and visited the Video wall of TMC and he explained about the process and working of it.
5 | 2019-06-27 | BTP | Mr.khan and Suresh | Jeevan | Visited social media dept of TMC,control room and discussed about the operations taken place by traffic dept.

## BDA
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions

## KFD
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions

## Generic Meetings
Sl No. | Date | Department | Officials Met | PMC Team Members | Discussions
| 2019-06-19 | BenSCL | Mr. Ravikumar, during HPSC Meeting | Shantveer and Ramya | To add data from Metro and Lakes Requested Suresh to arrange a trip to Bhopal, Pune and Chennai