## Sheet1
Sl No. | Phase 2 scoping of SWM | Remarks
1 | New Sensor Based bins to be placed across Bengaluru City | Meeting to be held along with SWM team and PMC to decide on the number and location.
2 | Regular litter bins are already available. These have to be integrated on a GIS map. Solution is requested to capture cleaning of these bins, eg. RFID cards. Latitude and Longitude of these bins are avialble for the old bins. No latitude and longitude available for the new bins. (Underground Bins also mapped) | Mail to be sent to SWM team to get the details on the Bins.
3 | CCTV integration - Around 400 CCTV cameras have been installed by the SWM department. These cameras to be integarted and control of these cameras to b avialbe in the ICCC SWM section. Also discussed on larger integartion -viewing of other cameras in Bengaluru City | Mail to be sent to SWM team, to get the details on the cameras - location, model, working conditions.
4 | Ward wised decentralisation plants , wet waste processing plant (7 centralised plants) should be monitored - Some of the solutions to be monitored are Vehicle entry (automatic entry with RFID), data integration with automated data on weigh bridges. Reports on count of vehicles, number of processed waste, number of composed waste, etc station wise and integrated data | All plants have their own software, the working condition and avilabilty of API to be checked and integrated.
5 | Future Integrations should also consider tracking of wates from Transfer Stations, DWCC(118 in operation), Sanitary Waste stations, Bulk Generation, Construction and Demolition Waste. Dump Points for BG and CnD should be available to citizens | Understand future pland and scalability of the project
6 | Picking of Waste should be monitored at house level or street level. Eg.RFID at each street or house. Ward No.112 has done a pilot project(check with Mr.Vishvesh or Krishna) | Contact Manjula for more details on project and contact numbers of Mr.Vishvesh or Krishna
7 | Fines collected from SWM to be tracked - Devices have been provided by HDFC. | The data to be integrated.
8 | BBMP Toilets - 130 toilets have been mapped on GIS - Feed back system is provided in these toilets - ITI is the vendor who has provided the hardware and software to track | Toilet Locator app to be checked. Check with ITI vendor to integarte data with ICCC SWM
9 | Dump Points for BG and CnD should be available to citizens. They are identifying locations to drop off regular waste too. ICCC should send messages to citizens on these locations
10 | Complaint Grievance System - They ae currently using Sahaya. Requested to check on workflow of different departments (process flow and SOP's).Advised to have a meeting with CGR heads to define minimum standards (SOP) | IGRMS will route the complaints to the BBMP Cell. Operations in the SWM will continue as it is with the SOP defined by them. IGRMS to have defined set of SOP's which will alerted in ICCC and escalated to different department heads
11 | CUG numbers of all officers to be added in the ICCC. These to act as escalation points and when acknowleding a ticket, the CUG numbers on the next level officers to be sent as a message | Understand on the policy and CUG number avaialabilty in all departments
ICCC should get to citizens - Dry waste and Cnd drop off points to citizens
even drop off on reguar waste
CUG - get juristidictional office
get all CUG numbers and add it in ICCC to get the escalation points